**QUARTERLY PROJECT STATUS REPORT**

**PROJECT SUMMARY**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| REPORT DATE | PROJECT  NAME | PROJECT  COORDINATORS | CHILDREN ENROLLED | TEACHERS EMPLOYED | ADMIN EMPLOYED |
| 16/1/2023 | IMESA Bangalore | Arshiya Khan | 45 | 1 qualified teacher.  1 coordinator and teacher.  1 support staff | Nil |

**STATUS SUMMARY**

Please provide summary of all the key achievements from the last quarter

**Objectives of the project**

The Project aimed to support the poorest Children in socio economically backward localities in Bangalore city.

The project helped in setting up the special classes at Al-Khair. The Children attended classes under supervision of two qualified teachers and a support staff.

90% of the students belong to very poor families of house maids, rickshaw pullers, labourer’s etc. Students from slums are also attending this class.

Number of beneficiaries:

The classes under the project started the strength of 5 students. Number of students increased to 45 students. These students belong to the poorest families of neighbouring areas.

**Capacity of beneficiaries before the project:**

Al-Khair had five studies before IMESA join. The children did not have proper facilities in their homes to study and do daily homework or prepare for exams. Their parents are not educated and could not help their work in basic studies. General atmosphere in these localities lack discipline and unless the children are given proper guidance, they fail in early classes and generally drop out of school.

**Brief methodology:**

The Project began on 1st August 2022 as local team got together and held meetings to prepare and plan the project. Campaign among local students and their parents began to join the free coaching and Guidance Centre. It look couple of weeks to make necessary preparation. Registration of students began within a day 45 students enrolled. Interview were held to appoint teachers and support staff. Qualified teachers were selected.

Coaching classes run between 4pm -8pm, five days a week.

Hindi, Urdu, English, Mathematics Social Study Science and general knowledge are taught in the class. Homework is done by the students with the help of teacher.

Extra-curricular activities and regular games kept students engaged for overall development Health tips are given by the teachers regularly. Islamic classes are held regularly on Fridays.

**BUDGET SUMMARY**

Please provide summary of all the expenses from the last quarter

|  |  |  |  |
| --- | --- | --- | --- |
| CATEGORY | SPENT | DATE | NOTES |
| Banners Printing and flyers | Sayeeda Saud spent for printing banners | 1 .8.2020 | Printed banners payment pending by Hamraah |

**RISK AND ISSUES SUMMARY**

Please provide summary of key risk and issues

|  |  |  |  |
| --- | --- | --- | --- |
| RISK / ISSUES | RAISED BY | STATUS | NOTES |
| Please see below | All staff | Need to be discuss with Executive in the quarterly meeting 16.1.2023 |  |

**CONCLUSION / RECOMMENDATIONS**

Please provide summary of all the key actions / improvements for next quarter

**Capacities Development in Beneficiaries after the Project**

The Centre is running’s smoothly from August 2022 – January 2023.

It helped greatly in improving performance of all the students. There is capacity to enrol more students.

We hope for the bright future of the students and successful result of the efforts of the official associated with the Bangalore.

**Further need for project**

It is vital that the project continues and students continue to get the support which is essential for their progress in studies. Without such support, student’s performance will deteriorate sharply effecting their results. Some of them may thus drop out.

They need financial support to pay for their fee from home to the school, and stationary notebooks, bags and off course the minimum school fees. The main reason of dropouts is that they could not meet their expenses. Lack of parental education seriously hinder their educational progress. Therefore the above coaching centre is essential to provide students support with their homework and exam preparation.

Strongly recommend to recruit qualified teachers for this IMESA need increase teacher’s salaries.

Indian Minority Education Society of Australia is convinced and is willing to offer ongoing support for the project. Bangalore team will continue running the classes for Muslim children.